## Sheet1
| 1 | 2 | 3 | 5 | 8 | 13 | 20+
references | Hello World Program | JS Pie Chart | Circle Comparator | Complexity Lab | Shapes Container | maze solver
| Make A Restaurant Receipt Using Command Line Input | check for overlapping ships | Board Games | 388 final module 2 | Web Search Using Linked List | pokemon database
| File I/O Practice | convert ships to tile arrays | JS Tabs | drawGrid | 388 final module 3 | 388 final project module 1 + reverse
stories
| test & implement normal shot | implement shot selection UI | Impl MedAI::placeShips | Create big shot function |  | Impl MedAI::makeMove
make Opponent Interface
points to hours conversion: | 0.5 hours/story point | estimated using time we took to complete low point stories, used higher point stories as sanity check
| 1 | 1 | 1 | 1 | 0 | 1
| 0 | 1 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
Total story points estimate | 26
Total hours estimate | 13